PRODUCT + ENGINEERING HANDOFF

Anticipy Hardware Development Brief

Custom PCB and investor-ready metal wearable  |  Rev 1  |  September 4, 2026

The job in one sentence Build a small, polished pendant that continuously captures useful speech, sends it to the Anticipy iPhone app, safely stores audio while the phone is unavailable, and gives discreet haptic feedback.

# Start here: what each person owns

## Omar / Anticipy provides

- The existing XIAO nRF52840 Sense boards used as the known working reference.

- Access to the current Anticipy iPhone test build and the current firmware/source or binary.

- A contact who can confirm the BLE UUIDs, packet format, codec, commands, and backfill behavior.

- The Anticipy logo, color direction, and a few exterior reference images.

## The hardware engineer owns

- System architecture, component selection, schematic, PCB layout, antenna/RF plan, power budget, and battery selection.

- Industrial/mechanical CAD, internal carrier, metal covers, acoustic openings, charging approach, tolerances, and assembly method.

- Prototype procurement, assembly, bring-up, firmware porting support, testing, design corrections, and production files.

- A clear written record of decisions, risks, costs, lead times, and what still needs approval.

## What success looks like

First success: one closed, pocketable, body-worn unit that works reliably with the real iPhone app and looks intentional from every angle.

Next success: three matching CNC-aluminum EVT units, each with a serial number and passed test record.

Then: a corrected Rev B design suitable for a ten-unit founder/investor batch.

Do not build these No camera, display, speaker, external daughterboards, loose stacked dev boards, taped-on parts, or a copied Plaud enclosure. The product must be recognizably Anticipy.

# 1. Product requirements

## The user experience

- The user wears Anticipy on a necklace or clip. It works ambiently; normal use should not require deliberate gestures.

- The microphones capture speech and firmware sends a mono audio stream to the Anticipy iPhone app over Bluetooth Low Energy.

- If the phone is temporarily unavailable, the pendant timestamps and stores compressed audio locally, then backfills in order when the phone returns.

- The app can command a short, discreet vibration. The device also reports battery, connection, storage, firmware, and health status.

- One subtle physical control is allowed for power, privacy/mute, pairing, or factory reset. Status light must be discreet, not visually dominant.

## Requirements matrix

| Area | Status | Requirement |
| --- | --- | --- |
| Camera/display/speaker | Fixed | None. |
| Phone | Fixed | iPhone is the primary companion and cloud gateway. |
| Connectivity | Fixed | Reliable BLE live audio, commands, status, reconnect, and ordered backfill. |
| Offline storage | Target | At least 16 hours of compressed audio; design for 20 hours with margin. |
| Battery life | Target | At least 16 hours in the real Anticipy use case, measured on a closed unit. |
| Size | Target | Aim for 51 x 21 x 11 mm. Do not exceed +10% per axis without written approval. |
| Weight | Target | Aim for 20 g or less. Flag any design above 25 g before fabrication. |
| Audio | Fixed | Clear body-worn conversational speech; no severe clothing-rub or haptic contamination. |
| Exterior | Fixed | Premium rounded pill, Anticipy branding, clean seams, no rattle, no exposed prototype wiring. |
| Durability | Target | Everyday sweat/splash resistance and 1 m drops; do not claim an IP rating before testing. |

Reference, not a copy Plaud NotePin/NotePin S is only the size-and-finish benchmark. Official specifications list 51 x 21 x 11 mm, about 17 g, two MEMS microphones, and an aluminum-alloy plus polycarbonate construction. Anticipy needs original geometry, branding, fastening, acoustic design, and internal architecture.

# 2. Electrical architecture and custom PCB

Recommended Rev A direction Keep the nRF52840 software family for the first custom board so the current XIAO firmware and iPhone integration are portable. Prefer a compact certified module if it materially lowers RF risk; use a bare SoC only if the engineer can own antenna tuning, certification risk, and schedule.

## Required functional blocks

MCU + BLE: nRF52840-compatible starting point; enough RAM/flash for codec, buffering, encrypted transport, DFU, and diagnostics.

Microphones: One or two low-power digital MEMS microphones. Prefer two footprints and populate based on measured benefit. Process to one outgoing mono stream.

Local storage: QSPI NOR flash sized from the actual codec. Plan 512 MB unless the calculation and wear model justify less.

Power: Protected Li-ion/LiPo, charger, power-path behavior, battery gauging, undervoltage protection, ESD, and measured current rails.

Haptics: Thin ERM or LRA plus a proper driver. It must be felt through clothing without resetting the radio or overwhelming the microphones.

Controls/status: One button or switch, discreet LED/light pipe if needed, and a reliable factory-reset path.

Charging/data: Preferred: sealed rear contacts and a small USB-C puck. Schedule fallback: a clean recessed USB-C port on Rev A.

Programming/test: SWD access, serial identity, test pads for rails/signals, current measurement, and a pogo fixture plan.

## Non-negotiable design work

- Capture the current BLE/app protocol before freezing the schematic: UUIDs, packet framing, timing, codec, commands, authentication, reconnect, backfill, and errors.

- Provide a measured power budget for live streaming, disconnected recording, idle, haptic, charging, and firmware update. Battery life is accepted only after a closed-unit test.

- Size storage using: bitrate x seconds / 8, then add at least 25% for metadata, filesystem overhead, bad sectors, logs, and wear. Example: 20 hours at 16 kbps needs about 180 MB with that margin.

- Keep the RF antenna and matching network away from battery, metal, ground pours, fast clocks, and the user-facing metal cover; include an RF test point or connector where practical.

- Add ESD protection, reverse-polarity/short protection, safe charge limits, and clear battery isolation. Never compress, bend, or trap a pouch cell.

- Store local audio encrypted, bind the pendant to its owner, support signed/validated firmware updates, and erase buffered audio only after confirmed transfer.

## Rev A PCB guidance

Board: 4-layer rigid PCB is the default. Use rigid-flex only if a real space or assembly benefit offsets cost and schedule.

Assembly: Prefer SMT parts on one side where possible, no hand-wired production connections, and explicit keep-outs for microphones, antenna, fasteners, battery, and charging contacts.

Firmware continuity: The custom board should preserve the existing app behavior. Any protocol change must be documented and agreed with the iOS developer before layout release.

# 3. Mechanical and industrial design

## Recommended construction

Fastest credible premium build Use a PC+ABS, MJF nylon, or SLA internal carrier that locates the PCB, battery, microphones, motor, contacts, and seals. Add CNC-machined 6061 aluminum front and back cosmetic covers. This gives a premium metal feel while protecting RF, acoustics, and assembly tolerances.

- Prototype the full internal stack and cover geometry in SLA before CNC. The printed assembly must close without pressure and pass audio, antenna, charging, haptic, and drop pre-tests.

- Keep a deliberate non-metal RF window adjacent to the antenna. Do not enclose the antenna inside a continuous metal box.

- Give each microphone a short, sealed acoustic path with mesh and gasket. Keep adhesive out of the port and isolate the mic from the motor and hard contact with the shell.

- Use hidden screws, snaps, or controlled adhesive joints. The enclosure must be openable during EVT without damaging the battery; no loose foam, rattling parts, or tape visible from outside.

- Provide compliant battery clearance, a rigid protective bridge if parts stack above it, strain relief for leads, and no sharp edges or point loads near the pouch.

- Include an intentional chain passage or clip interface. It must not weaken the shell, block microphones, or sit inside the antenna keep-out.

- Model assembly order, tool access, tolerance stack, adhesive thickness, gasket compression, and cable bend radii. Nominal fit alone is not enough.

## Material and finish decision

| Part | Rev A recommendation | Reason |
| --- | --- | --- |
| Outer covers | CNC 6061-T6 aluminum, bead-blasted + anodized | Fast, repeatable, premium, lighter and easier to machine than titanium. |
| Internal carrier | Black or natural PC+ABS / MJF PA12 / engineering SLA | Controls fit, creates RF window, locates components, and isolates the battery. |
| Acoustic seal | Purpose-made mesh + thin silicone gasket | Protects the port while maintaining a repeatable sound path. |
| Battery pad | Thin flame-rated or specified pressure-sensitive material | Prevents movement without squeezing the pouch. |
| Titanium | Evaluate after Rev A passes | Use only if weight, RF, machining cost, finish, and lead time are proven acceptable. |

## Exterior quality bar

- Original Anticipy silhouette; compact rounded pill, not a clone of another product.

- Even seam and finish, clean logo, no sharp edges, no visible glue squeeze-out, no exposed layer lines, and no audible rattle.

- Charging, microphone, button, LED, and chain features must look intentional and be located from the complete internal stack, not added afterward.

# 4. How we will build it

## Checkpoint A: 24-48 hour engineering audition

Purpose Before expensive fabrication, show how you think. Do not merely redraw the old prototype. Identify contradictions, make recommendations, and quantify the risks.

- One system block diagram and a written architecture recommendation.

- Current XIAO/app compatibility plan, including what must be measured or captured from the existing firmware.

- Preliminary BOM with manufacturer part numbers, size, cost, availability, lifecycle status, and at least one substitute for critical parts.

- Power and storage calculations with best/expected/worst cases.

- Preliminary PCB outline/stack and a mechanical cross-section showing the complete component stack.

- Recommended material/finish, charging method, prototype quantities, schedule, estimated cost, and top ten risks.

- A short list of requirement exceptions. Every exception must explain why and propose a specific alternative.

## Checkpoint B: prove the electronics

- Reproduce the current XIAO-to-iPhone audio flow and record the protocol as the baseline.

- Bring up the Rev A custom PCB on the bench: power, charging, microphones, BLE, storage, haptics, button, LED, DFU, and diagnostic logging.

- Run power, RF, audio, haptic-noise, storage/backfill, charging, and thermal tests before enclosing it.

## Checkpoint C: prove the enclosure

- Print one complete SLA/MJF fit unit using the real PCB, real battery, real motor, real fasteners, real gaskets, and real adhesive thickness.

- Fix fit, acoustic, antenna, haptic, charging, and assembly issues in the printed unit.

- Only then release CNC drawings for three 6061-aluminum EVT units.

## Checkpoint D: close the unit and test it

- Assemble three serialized EVT units using the documented process.

- Test each unit closed, body-worn, with the real iPhone app. Record every result and failure.

- Correct the design into Rev B. Freeze files only after all release gates pass.

## Checkpoint E: ten-unit founder/investor batch

Build only after approval: ten matching Rev B units plus spares using the same BOM revisions, material/finish specifications, firmware version, assembly process, and test record.

# 5. What the engineer must hand back

## Electrical design package

- Native schematic and PCB source files, schematic PDF, board STEP model, fabrication drawings, stack-up, controlled-impedance notes, Gerbers or ODB++, drill files, IPC netlist, pick-and-place, and assembly drawings.

- BOM with exact manufacturer part numbers, approved substitutes, distributor links, pricing at 1/10/100/1,000 units, lifecycle and availability notes.

- Antenna layout/keep-out and RF test plan; power-tree diagram; charger/protection details; test-point map; programming and production-test fixture design.

- Board bring-up checklist, measured current table, known issues, engineering changes, and revision history.

## Mechanical design package

- Native CAD plus STEP for the full assembly and every manufactured part.

- Dimensioned 2D drawings with tolerances/GD&T, material, finish, color, surface texture, thread/fastener notes, gasket/adhesive specification, and critical-to-quality dimensions.

- Exploded view, assembly order, cross-sections, tolerance-stack report, mass properties, antenna/acoustic keep-outs, and battery no-pressure clearance proof.

- Print-ready fit-check files, CNC RFQ pack, and a vendor-ready inspection checklist.

## Firmware and interface package

- Source repository, build instructions, pin map, release binary, version/hash, bootloader/DFU procedure, factory-reset path, and recovery steps.

- BLE protocol document: services/characteristics, codec, packet format, timestamping, acknowledgements, encryption/owner binding, commands, backfill, error codes, and version compatibility.

- Manufacturing test firmware plus a normal diagnostic mode that reports mic, flash, battery, charging, haptic, button, radio, reset cause, and firmware version.

## Manufacturing and QA package

- Supplier list, quotes, lead times, minimum order quantities, approved materials, incoming inspection, assembly SOP, rework limits, and shipping/battery paperwork.

- One serial-numbered test record per unit, photographs of the closed unit, measured dimensions/weight, and a signed release checklist.

- Everything must be editable source, not screenshots or flattened exports only. Anticipy receives all project files and credentials needed to reproduce the build.

Important release rule A beautiful enclosure is not a working unit. A working board in a rough shell is not an investor unit. Both the closed hardware and the real Anticipy app flow must pass together.

# 6. Acceptance tests for each EVT unit

| Gate | Pass condition |
| --- | --- |
| App + BLE | Owner pairing succeeds; reconnect is automatic; control cannot silently transfer to a second phone; live audio, status, commands, and backfill work with the current app. |
| Audio | Body-worn quiet-room and normal-conversation recordings are intelligible; no severe RF ticks, charging noise, clothing rub, occlusion, or haptic contamination. |
| Storage | A forced disconnection fills and backfills the intended buffer in correct time order with no duplicate, missing, or corrupt segments. Capacity meets the agreed 16-20 hour target. |
| Battery | Measured closed-unit run time meets the agreed 16-hour use-case target; gauge and low-battery behavior are predictable; no unexpected reset or deep discharge. |
| Charging/thermal | Safe charge current and termination are verified. Cell and surface temperatures remain within the battery vendor limits and the agreed skin-contact limit during charge and use. |
| Haptics | 100 commanded pulses work without brownout, disconnect, loose parts, or unacceptable microphone contamination. |
| RF | Stable body-worn operation at 5 m and room-scale operation at 10 m in the agreed test environment; antenna performance is checked with metal covers installed. |
| Mechanical | Meets approved size/weight; no pressure on the battery; even seams; no rattle; charging/controls/attachment work after drop and handling tests. |
| Drop/handling | Passes the agreed 1 m multi-face drop sequence, charging-contact cycles, chain/clip pull, shake, and light torsion tests without opening or losing function. |
| Security/update | Local audio is encrypted; owner binding works; firmware update and recovery work; reset procedure is intentional and documented. |

## Stop conditions

- Do not close or ship a unit if the battery is squeezed, punctured, hot, unprotected, undocumented for transport, or able to move inside the enclosure.

- Do not release CNC if the complete SLA fit unit has not passed closure, audio, RF, charge, haptic, and battery-clearance checks.

- Do not build ten if any of the three EVT units needs a different hand-fitted fix. Correct the CAD/PCB/process first.

- Do not claim waterproofing, battery life, range, or certification from calculations alone. Test and record it.

# 7. Decisions the engineer should recommend

These are not homework for Omar before kickoff. The engineer should present a recommendation, evidence, cost, and schedule impact for each item at Checkpoint A.

MCU implementation: nRF52840 module vs. bare SoC vs. another compatible low-power BLE platform.

Microphone count: One vs. two digital MEMS microphones based on actual transcription and noise tests.

Audio transport: Codec, frame size, BLE throughput, retransmission, buffering, clock/timestamp strategy, and iOS background behavior.

Storage: Flash type/capacity and wear strategy that meet 16-20 hours with the selected codec.

Battery: Capacity, dimensions, protected cell/pack, supplier, certification, run time, charging current, and enclosure clearance.

Charging: Sealed contact puck vs. clean recessed USB-C for Rev A, including ESD and mechanical life.

Haptics: ERM vs. LRA, driver, mounting, feel, current, and acoustic contamination.

Materials: 6061 aluminum Rev A; whether titanium adds enough value to justify its weight, RF, machining, cost, and schedule effects.

Attachment: Chain passage, clip, magnetic accessory, and how it affects acoustics, RF, strength, and size.

Environmental target: Realistic splash/sweat sealing and the validation path before making any IP claim.

## What is out of scope for this first hardware engagement

- Cloud AI behavior, app redesign, BCI/EMG add-ons, cameras, displays, speakers, and gesture-driven interaction.

- Injection-mold tooling or large production orders before the Rev B design and test process are frozen.

- Titanium mass production before the aluminum EVT design passes and a specific titanium RF/mechanical plan is approved.

# Omar: your only four actions

- Send this brief to the hardware engineer.

- Hand him two XIAO nRF52840 Sense boards and give him access to the Anticipy iPhone test build/current firmware.

- Send the Anticipy logo plus the preferred color/finish images.

- Ask him to return Checkpoint A within 24-48 hours. Approve fabrication only after that review.

The exact kickoff message “Please read the attached Anticipy hardware brief. Start with Checkpoint A and tell me where the requirements conflict or create risk. I want your recommended architecture, preliminary BOM, power/storage math, PCB outline, enclosure cross-section, schedule, cost, and top risks before we release any PCB or CNC order.”